## Jira Backlog
Issue ID | User Story / Task | Description | Story Points | Team Member | Branch Name | Priority | Status
TR-0 | Task | Create SRS Jira Task Sheet, Presentation, Final Report | 4 | Amit | document-setup | High | To Do
TR-1 | Task | Initialize Flask project and repository structure | 3 | Amit | feature/project-setup | High | To Do
TR-2 | Task | Create HTML page with input box and translate button | 5 | Amit | feature/frontend-ui | High | To Do
TR-3 | Task | Create Flask route to accept English text input | 5 | Amit | feature/flask-api | High | To Do
TR-4 | Task | Integrate Helsinki-NLP opus-mt-en-hi model using transformers | 8 | Amit | feature/model-integration | High | To Do
TR-5 | Task | Process input text and return Hindi translation | 5 | Amit | feature/translation-logic | Medium | To Do
TR-6 | Task | Handle empty input and server errors | 3 | Amit | feature/error-handling | Medium | To Do
TR-7 | Task | Display translated Hindi output on webpage | 3 | Amit | feature/output-display | Medium | To Do
TR-8 | Task | Unit testing for translation API and UI | 5 | Amit | feature/testing | Medium | To Do
TR-9 | Task | Containerize application for deployment | 5 | Amit | feature/docker-setup | Low | To Do
TR-10 | Task | Deploy Flask application on Render platform | 3 | Amit | feature/render-deployment | High | To Do
TR-11 | Task | Write README and SRS documentation | 2 | Amit | docs/project-documentation | Low | To Do
TR-12 | Task | Optimize model loading and response time | 5 | Amit | feature/performance | Medium | To Do